## Sheet1
Implementation Period - 12 Months
Project Role | No. of Resources | Duration (Months) | Total Man-Month | Role (As per NeGD) | Rate in INR (As per NeGD) | Total Cost in INR
Project Manager | 1 | 12 | 12 | Category A - Program Manager (PrM) | 357706.64 | 4292479.68
Solution Architect | 1 | 3 | 3 | Category B - Solution Architect (SA) | 429247.35 | 1287742.05
Business Analyst | 1 | 3 | 3 | Category A - Senior Consultant (SC) | 327897.41 | 983692.23
Domain Expert - Architect | 1 | 6 | 6 | Category A - Senior Consultant (SC) | 327897.41 | 1967384.46
UI/UX Designer | 1 | 4 | 4 | Category C - Technology Consultant (TC) | 280203.26 | 1120813.04
Sr. Backend Developer | 1 | 10 | 10 | Category C - Senior Technology Consultant (TSC) | 327897.41 | 3278974.1
Sr. Frontend Developer | 1 | 10 | 10 | Category C - Senior Technology Consultant (TSC) | 327897.41 | 3278974.1
Backend Developer | 2 | 10 | 20 | Category C - Technology Consultant (TC) | 280203.26 | 5604065.2
Frontend Developer | 2 | 10 | 20 | Category C - Technology Consultant (TC) | 280203.26 | 5604065.2
Tester | 1 | 4 | 4 | Category A - Senior Consultant (SC) | 327897.41 | 1311589.64
DevOps Engineer | 1 | 6 | 6 | Category C - Technology Consultant (TC) | 280203.26 | 1681219.56
Total Cost (Without GST) | [5 empty] | 30410999.26
@18% GST | [5 empty] | 5473979.8668
Total cost (With GST) | [5 empty] | 35884979.1268
Hypercare Period - 12 Months
Project Role | No. of Resources | Duration (Months) | Total Man-Month | Role (As per NeGD) | Rate in INR (As per NeGD) | Total Cost in INR
Project Manager | 1 | 6 | 6 | Category A - Program Manager (PrM) | 357706.64 | 2146239.84
Business Analyst cum Tester | 1 | 3 | 3 | Category A - Senior Consultant (SC) | 327897.41 | 983692.23
Domain Expert - Architect | 1 | 6 | 6 | Category A - Senior Consultant (SC) | 327897.41 | 1967384.46
UI/UX Designer | 1 | 2 | 2 | Category C - Technology Consultant (TC) | 280203.26 | 560406.52
Sr. Backend Developer | 1 | 6 | 6 | Category C - Senior Technology Consultant (TSC) | 327897.41 | 1967384.46
Sr. Frontend Developer | 1 | 6 | 6 | Category C - Senior Technology Consultant (TSC) | 327897.41 | 1967384.46
Backend Developer | 1 | 12 | 12 | Category C - Technology Consultant (TC) | 280203.26 | 3362439.12
Frontend Developer | 1 | 12 | 12 | Category C - Technology Consultant (TC) | 280203.26 | 3362439.12
DevOps Engineer | 1 | 6 | 6 | Category C - Technology Consultant (TC) | 280203.26 | 1681219.56
Total Cost (Without GST) | [5 empty] | 17998589.77
@18% GST | [5 empty] | 3239746.1586
Total cost (With GST) | [5 empty] | 21238335.9286
O&M Period - 36 Months
Project Role | No. of Resources | Duration (Months) | Total Man-Month | Role (As per NeGD) | Rate in INR (As per NeGD) | Total Cost in INR
Project Manager | 1 | 18 | 18 | Category A - Program Manager (PrM) | 357706.64 | 6438719.52
Business Analyst cum Tester | 1 | 9 | 9 | Category A - Senior Consultant (SC) | 327897.41 | 2951076.69
Domain Expert - Architect | 1 | 18 | 18 | Category A - Senior Consultant (SC) | 327897.41 | 5902153.38
UI/UX Designer | 1 | 3 | 3 | Category C - Technology Consultant (TC) | 280203.26 | 840609.78
Sr. Backend Developer | 1 | 6 | 6 | Category C - Senior Technology Consultant (TSC) | 327897.41 | 1967384.46
Sr. Frontend Developer | 1 | 6 | 6 | Category C - Senior Technology Consultant (TSC) | 327897.41 | 1967384.46
Backend Developer | 1 | 36 | 36 | Category C - Technology Consultant (TC) | 280203.26 | 10087317.36
Frontend Developer | 1 | 36 | 36 | Category C - Technology Consultant (TC) | 280203.26 | 10087317.36
DevOps Engineer | 1 | 18 | 18 | Category C - Technology Consultant (TC) | 280203.26 | 5043658.68
Total Cost (Without GST) | [5 empty] | 45285621.69
@18% GST | [5 empty] | 8151411.9042
Total cost (With GST) | [5 empty] | 53437033.5942

## Sheet2
S.N. | Role for resource | Rates* in Rupees Per Month (Without GST) | Rates* in Rupees Per Month & As per Latest Corrigendum (3% increase) (Without GST)
Category A: Scope of work - Project/Programme Management and Advisory services
1 | Project Manager (PM) | 318347 | 327897.41
2 | Program Manager (PrM) | 347288 | 357706.64
3 | Portfolio Manager (PoM) | 405169 | 417324.07
4 | Associate Consultant/ Business Analyst (BA) | 231525 | 238470.75
5 | Consultant (C) | 272042 | 280203.26
6 | Senior Consultant (SC) | 318347 | 327897.41
7 | Principal Consultant (PC) | 347288 | 357706.64
8 | Management Consultant (MC) | 385875 | 397451.25
9 | Subject Matter Expert (SMEl) | 347288 | 357706.64
10 | Subject Matter Expert (SME2) | 347288 | 357706.64
Category B: Scope of work - Domain or cross-domain specific architecture for Digital Ecosystem, Enterprise, and Solutions
1 | Associate Solution Architect (ASA) | 380000 | 391400
2 | Solution Architect (SA) | 416745 | 429247.35
3 | Senior Solution Architect (SSA) | 486203 | 500789.09
4 | Functional/ Business Architect (BAI) | 416745 | 429247.35
5 | Functional/ Business Architect (BA2) | 486203 | 500789.09
6 | Enterprise Architect (EA1) | 416745 | 429247.35
7 | Enterprise Architect (EA2) | 486203 | 500789.09
Category C: Scope of work - Technology management and adoption of Emerging Technologies
1 | Associate Technology Consultant (TAC) | 225000 | 231750
2 | Technology Consultant (TC) | 272042 | 280203.26
3 | Senior Technology Consultant (TSC) | 318347 | 327897.41
4 | Principal Technology Consultant (TPC) | 347288 | 357706.64
5 | Management Technology Consultant (TMC)* | 385875 | 397451.25
6 | Associate in Al/ML/RPA/Data Science (AAl) | 250000 | 257500
7 | Lead in Al/ML/RPA/Data Science (LAI) | 325000 | 334750
8 | Expert in Al/ ML/RPAl Data Science (EAl) | 400000 | 412000
9 | Associate in Blockchain (AB) | 300000 | 309000
10 | Lead in Blockchain (LB) | 330000 | 339900
11 | Expert in Blockchain (EB) | 400000 | 412000
. .